## Sheet1
| Date | Descripton | Parties Involved
Pre Campaign Planning
| Fall 2018 | Pre-Screen Community | AD/Booster/Coaches
| 2019-01-01 | Superintentent/BOE Presentation | AD/Central Admin
| 2019-02-01 | Develop Board of Directors | AD/Community Leaders
| Spring 2019 | Begin Prospect Relationships | AD/Capital Board
| 2019-04-01 | Define Project | AD/Capital Board/Staff
| 2019-05-01 | Draft Case Statement | Steering Committee
Planning Phase
| Summer 2019 | Finalize Case | BOD
| 2019-09-01 | Organize Committee Rosters | BOD
| 2019-10-01 | Develop Timeline | Planning Committee
| 2019-11-01 | Create Donor Recognition Plan | Resource Committee/BOD
| 2019-12-01 | Develop Soliciation Strategy | Resource Committee/BOD
Quiet Phase
| 2020-02-01 | Host Donor Meeting Sessions | AD/Steering Committee
| 2020-03-01 | Conduct Walking Tours | Steering Committee
| April/May 2020 | Solicite Large Gifts | Resource Committee/BOD
| Summer 2020 | Review and Revise Plan | BOD/AD
| Summer 2020 | Plan Kick Off | Planning Committee
Kick Off
| 2020-08-01 | Develop Media - Website/Brochure | Steering Committee
| 2020-09-01 | Announce Project Publically | Steering Committee
| Sept/Oct 2020 | Market | Steering Committee
| Cot 2020 | Marketing | Steering Committee
Public Phase
| 2020-10-01 | Soliciat Mid-Level Gifts | Planning Committee
| 2020-11-01 | Solicit Membership Gifts | Planning Committee
| 2020-11-01 | Host Contribution Events/Mailings/Emails | Planning Committee
Follow-Up
| Spring 2021 | Celebrate Goal Achievement | Planning Committee/BOD
| ??? | Celebrate Project Completion | AD/Steering Committee